Annual Action Plan, 2022

| 2022 Annual Action Plan for Karaga District Assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Adopted Goal: Maintain a stable, united and safe society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MDA Programmes and Sub-programmes | Activities (Operations) |  | Location |  | Baseline |  |  | Output Indicators |  | Quarterly Time schedule |  |  |  |  |  |  |  |  | Indicative Budget |  |  |  |  | Implementing Agencies |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | 1st |  | 2nd |  |  | 3rd |  | 4th |  | GoG |  | IGF | Donor |  | Lead |  |  |  | Collaborating |  |  |
| Management and Administration (GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY DIMENSION) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General Administration | Organize and service general and subcommittee meetings of the assembly |  | District Assembly |  |  |  |  |  | Number of general & sub-committee meetings organized | x |  | x |  |  | x |  | x |  | 15,000.00 |  |  |  |  | DPCU |  |  |  | DA |  |  |
|  | Pay non established labor[casual labor] |  | District Wide |  |  |  |  |  | Number of non-established labor paid | x |  | x |  |  | x |  | x |  |  |  | ,000.00 |  |  | DPCU |  |  |  | DA |  |  |
|  | Public sensitization on NACAP |  | District wide |  |  |  |  |  | Number of sensitizations exercise organized | x |  | x |  |  | x |  | x |  |  |  | 9,200 |  |  | DPCU |  |  |  | DA |  |  |
|  | Maintenance of website |  | karaga |  |  |  |  |  | Website designed |  |  | x |  |  | x |  |  |  | 2000 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Payment of electricity bills |  | karaga |  |  |  |  |  | Bills of Assembly paid | x |  | x |  |  | x |  | x |  | 9000 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Repair and maintain office vehicles |  | Karaga |  |  |  |  |  | Office vehicles repaired and maintained | x |  | x |  |  | x |  | x |  | 20,000.00 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Procure repair and replacement of office equipment |  | District Assembly |  |  |  |  |  | Office equipment repaired and replaced | x |  | x |  |  | x |  | x |  | 70,000.00 |  |  | RING |  | DA |  |  |  | DA |  |  |
|  | Organize monthly DISSEC meetings |  | District Assembly |  |  |  |  |  | Number of DISSEC meetings organized | x |  | x |  |  | x |  | x |  |  |  | 5,000.00 |  |  | DA |  |  |  | DA |  |  |
|  | Seminars and conferences |  | District Assembly |  |  |  |  |  | Serminars and conferences attended | x |  | x |  |  | x |  | x |  | 30,000.00 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Support to traditional authority |  | District Wide |  |  |  |  |  | Traditional authority supported | x |  | x |  |  | x |  | x |  | 20,000.00 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Assembly's contribution to NALAG and regional programs |  | Karaga |  |  |  |  |  | Amount of funds contributed to NALAG programmes | x |  | x |  |  | x |  | x |  | 30,000.00 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Manage security within the District |  | District Wide |  |  |  |  |  | Security within the District managed | x |  | x |  |  | x |  | x |  | 100,000.00 |  |  |  |  | Sec. Service |  |  |  | DA |  |  |
|  | Organize and service all national celebrations |  | Karaga |  |  |  |  |  | Number of national celebrations organized | x |  | x |  |  | x |  | x |  | 30,000.00 |  |  |  |  | D/A |  |  |  | NGOs & Depts. |  |  |
| Finance and Revenue Mobilization | Procure value books for IGF mobilization |  | District Assembly |  |  |  |  |  | Value books procured for revenue mobilization | x |  | x |  |  |  |  |  |  |  |  | 1,000.00 |  |  | DA |  |  |  | DA |  |  |
|  | Monitor revenue mobilization |  | District Wide |  |  |  |  |  | Revenue mobilization in the District increased | x |  | x |  |  | x |  | x |  |  |  | 4,000.00 |  |  | DA |  |  |  | DA |  |  |
|  | Submission of monthly financial reports |  | Karaga |  |  |  |  |  | Number of monthly financial reports submitted | x |  | x |  |  | x |  | x |  | 3,000.00 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Cede IGF collected to Area Councils to make them functional |  | Area Councils |  |  |  |  |  | Amount of funds ceded to Area Councils | x |  | x |  |  | x |  | x |  |  |  | 10,000.00 |  |  | DA |  |  |  | DA |  |  |
| Planning, Budgeting and Coordination | Organize fee-fixing consultations with tax payers at the area council and district levels |  | Area Councils |  |  |  |  |  | Fee fixing consultations with tax payer at the A/Cs and District levels organized |  |  |  |  |  | x |  | x |  | 9,000.00 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Production workshop on composite budget |  | Karaga |  |  |  |  |  | Production workshop on composite budget organized |  |  |  |  |  | x |  | x |  | 4,000.00 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Participate in regional budget hearing for 2022 |  | Karaga |  |  |  |  |  | 2019 budget hearing organized |  |  |  |  |  | x |  | x |  | 6,000.00 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Organize quarterly DPCU and budget committee meetings |  | Karaga |  |  |  |  |  | Quarterly DPCU and BC meetings organized | x |  | x |  |  | x |  | x |  | 4,000.00 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Publicize and advertise District Assembly projects and programmes |  | District Assembly |  |  |  |  |  | Number of adverts made on projects and programmes in the year | x |  | x |  |  | x |  | x |  | 15,000.00 |  |  |  |  | DA |  |  |  | DA |  |  |
|  | Preparation of 2022-2025 MTDP |  | Karaga |  |  |  |  |  | Number of MTDP producde |  |  | x |  |  |  |  |  |  |  |  |  | 15,000 |  |  |  |  |  | DA |  |  |
|  | Conduct coordinated monitoring visits by DPCU |  | District Wide |  |  |  |  |  | Coordinated monitoring visits conducted | x |  | x |  |  | x |  | x |  |  |  |  | 4,000.00 |  | RING |  |  |  | DA |  |  |
|  | Monitoring of physical project |  | Project locations |  |  |  |  |  | Monitoring activities carried | x |  | x |  |  | x |  | x |  |  |  | 19,000 |  |  | DPCU |  |  |  | DA |  |  |
|  | Organize 2No. Town hall meetings |  | District Wide |  |  |  |  |  | Number of town hall meetings organized |  |  | x |  |  | x |  |  |  | 10,000. |  |  |  |  | DA |  |  |  | DPCU/ Depts. |  |  |
| Human Resource Management | Training of key officers on filling and recording systems |  | Kagara DA |  |  |  |  |  | Key Officers knowledge on filling and recording improved | x |  | x |  |  |  |  |  |  |  |  |  |  |  | DA |  |  |  | HR Dpt |  |  |
|  | Training of key staff on asset management |  | District Assembly |  |  |  |  |  | Knowledge of officers on asset management improved |  |  | x |  |  | x |  |  |  |  |  | 11,450 |  |  | DA |  |  |  | HR Dpt |  |  |
|  | Training of all heads of department on project management |  | Karaga DA |  |  |  |  |  |  |  |  |  |  |  | x |  | x |  |  |  | 11,450 |  |  | DA |  |  |  | HR Dpt |  |  |
|  | Train heads of decentralized department on public financial management |  | District Assembly |  |  |  |  |  |  | x |  | x |  |  |  |  |  |  |  |  | 11,450 |  |  | DA |  |  |  | HR Dpt |  |  |
|  | Training of key officers in all Dpts of the Assembly on Local Government service delivery standards |  | District Assembly |  |  |  |  |  | Knowledge on Local Government service delivery standards improved | x |  | x |  |  |  |  |  |  |  |  | 11,450 |  |  | DA |  |  |  | HR Dpt |  |  |
|  | Training of all heads of Dept on Local Government protocol |  | Karaga DA |  |  |  |  |  | Heads of Depts Knowledge on Local government protocols |  |  |  |  |  | x |  | x |  | 6000 |  |  |  |  | DA |  |  |  | HR Dept |  |  |
|  | Organize monthly DISSEC meetings |  | karaga |  |  |  |  |  | DISSEC meetings held | x |  | x |  |  | x |  | x |  | 5000 |  |  |  |  | DA |  |  |  | DA |  |  |
| Adopted Goal: Safeguard the natural environment and ensure a resilient built environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Physical and Spatial Planning |  | Carry out street naming and property addressing system in the District |  | District Wide |  |  |  |  | street naming and property addressing system carried out |  | x |  | x | x |  | x |  | 80,000.00 |  |  |  |  |  |  |  | D/A |  |  | DA |  |
|  |  | Facilitate the preparation of one local plan for growing business center of karaga |  | Karaga 1 |  |  |  |  | Five local plans developed |  | x |  | x |  |  |  |  | 50,000 |  |  |  |  |  |  |  | PPD |  |  | KDA, chief and Assembly members |  |
|  |  | Organize monthly Statutory Planning Committee meetings and Technical Sub-committee meeting to hasten the permitting process |  | District wide |  |  |  |  | Statutory planning committee and Technical committee meeting organised |  |  |  |  | x |  | x |  | 20000 |  |  |  |  |  |  |  | PPD |  |  | KDA/statutory planning committee members |  |
|  |  | Install 10 street signage plate |  | Karaga, |  |  |  |  | 10 street signage plates installed |  | x |  | x |  |  |  |  | 20000 |  |  |  |  |  |  |  | PPD |  |  | KDA, Chiefs and Assembly members |  |
|  |  | Install 500 property plate |  | Karaga, |  |  |  |  | 500 property plates installed |  |  |  |  |  |  |  |  | 15000 |  |  |  |  |  |  |  | PPD |  |  | KDA, Chiefs and Assembly persons |  |
|  |  | Facilitate the acquisition and documentation of 6 no. public land uses |  | District wide |  |  |  |  | 6 public land acquired documented |  |  |  | x | x |  |  |  | 20,000,00 |  |  |  |  |  |  |  | PPD |  |  | KDA, Chiefs and Assembly members |  |
|  |  | Construction of speed Humps |  | karaga |  |  |  |  | Three speed rumps construted |  | x |  | x | x |  | x |  | 12,000 |  |  |  |  |  |  |  | DWD |  |  | DA |  |
|  |  | Erection maintenance of road sign psts |  | karaga |  |  |  |  | Sign posts erected |  | x |  | x |  |  |  |  | 9,000 |  |  |  |  |  |  |  | DWD |  |  | DA |  |
|  |  | Visibility improvement (vegetation control) |  | karaga |  |  |  |  | Vegetation cleared |  | x |  | x | x |  | x |  | 28,000 |  |  |  |  |  |  |  | DWD |  |  | DA |  |
|  |  | Pot hole Patching |  | karaga |  |  |  |  | Pot holes patched |  | x |  | x | x |  |  |  | 13,000 |  |  |  |  |  |  |  | DWD |  |  | DA |  |
| Infrastructure Development |  | Reshaping of roads (6.80km) |  | Gbutugu-yilang |  |  |  |  | KMs of feeder roads reshaped |  | x |  | x | x |  | x |  |  |  |  |  |  | 99,298.00 |  |  | D/A |  |  | Feeder Roads |  |
|  |  | Shaping of Yilang – Tublizee Feeder Road (4.20km) |  | Yilang, Tublizee |  |  |  |  | 4.20 km road reshaped |  |  |  | x | x |  |  |  |  |  |  |  |  | 113,000 |  |  | DWD |  |  | Feeder roads |  |
|  |  | Re-shaping of Karaga Girls Model School Junction to the school and others (3.00km) |  | D/A, Karaga Girls Model School and others |  |  |  |  | Girls model school reshaped |  | x |  | x | x |  | x |  |  |  |  |  |  | 85,386 |  |  | DWD |  |  | DA |  |
|  |  | Shaping of Tanyeli – Nanduli Feeder Road (5.00km) |  | Tanyeli, Nanduli |  |  |  |  | 5.00km road reshaped |  |  |  |  | x |  | x |  |  |  |  |  |  | 125,000 |  |  | DWD |  |  | DA |  |
|  |  | Support to community initiated project |  | District Wide |  |  |  |  | Number of projects supported |  | x |  | x | x |  | x |  |  |  | 80,000 |  |  |  |  |  |  |  |  |  |  |
|  |  | Construction and furnishing of 1No CHPS Compound |  | Kpasong |  |  |  |  | CHPS compound constructed |  |  |  | x | x |  |  |  |  |  | 361,359.10 |  |  |  |  |  | DWD |  |  | DA |  |
|  |  | Construction of 1No 3-unit classroom block with ancillary facilities |  | Takalgu |  |  |  |  | Classroom block constructed |  |  |  | x | x |  |  |  |  |  | 232,879.39 |  |  |  |  |  | DWD |  |  | DA |  |
|  |  | Construction and drilling of 3 no. mechanised boreholes |  | Selected communities |  |  |  |  | Boreholes constructed |  | x |  | x | x |  |  |  |  |  | 70,000 |  |  |  |  |  | DWD |  |  | DA |  |
|  |  | Rehabilitation of 1No. 6-Unit Classroom Block with Office and Store |  | Karaga D/A primary A |  |  |  |  | School block renovated |  |  |  | x | x |  |  |  |  |  | 79,407.00 |  |  |  |  |  | DWD |  |  | DA |  |
|  |  | Renovate 2No. School Building at Ishadia Girls School and Tong D/A Primary School |  | Karaga, Tong |  |  |  |  | School block renovated |  |  |  | x | x |  |  |  |  |  | 151,197.00 |  |  |  |  |  | Global communities |  |  | DA |  |
|  |  | Rehabilitate 4No. Staff quarters |  | Karaga |  |  |  |  | 4No. Staff quarters rehabilitated |  | x |  | x | x |  |  |  | 64,000.00 |  |  |  |  |  |  |  | DA |  |  | DA/WD |  |
|  |  | Maintenance of office facilities |  | Karaga |  |  |  |  | Office facilities maintained |  | x |  | x | x |  | x |  |  |  | 36,000.00 |  |  |  |  |  | DA |  |  | DA/WD |  |
| Adopted Goal: Create opportunities for all |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Education and Youth Development |  | Supply of 65No. Dual Desk Furniture to 3No. Basic Schools |  | Nyong Nayili Waterjeep, Sadugu Primary and Karaga D/A |  |  |  |  | Dual Desks supplied |  | x |  | x |  |  |  |  |  |  | 19,467.7 |  |  |  |  | DA |  |  |  | DA |  |
|  |  | Procure and supply 255No. Dual desks 10 Teachers tables |  | Takalgu Ishdia |  |  |  |  | 800no. Dual desks for basic schools procured & supplied |  | x |  | x | x |  |  |  |  |  | 83,000.00 |  |  |  |  | DWD |  |  |  | DA |  |
|  |  | Support monitoring of education service delivery |  | District Wide |  |  |  |  | Monitoring of education service delivery supported |  | x |  | x | x |  | x |  | 15,000.00 |  |  |  |  |  |  | DA |  |  |  | DA/WD |  |
|  |  | Construct and furnish 3unit classroom block and ancillaries at Sadugu |  | Sadugu |  |  |  |  | 1No. 3unit Classroom Block Constructed |  | x |  | x | x |  | x |  | 200,000.00 |  |  |  |  |  |  | DA |  |  |  | DA/WD |  |
|  |  | Re-roofing of stormed rift off schools |  | District Wide |  |  |  |  | Number of rift off schools roofed |  | x |  | x | x |  | x |  | 70,000.00 |  |  |  |  |  |  | DA |  |  |  | DA/WD |  |
|  |  | Construct and furnish 3-unit classroom block and ancillary facilities at Karaga Girls Model JHS |  | Karaga |  |  |  |  | 1No. 3unit Classroom Block Constructed |  | x |  | x | x |  | x |  | 200,000.00 |  |  |  |  |  |  | DA |  |  |  | DA/WD |  |
|  |  | Support to needy students under MP's DACF fund |  | District Wide |  |  |  |  | Number students supported |  | x |  | x | x |  | x |  | 42,057.38 |  |  |  |  |  |  | MP |  |  |  | DA |  |
|  |  | Support to basic schools debates, reading & quiz competitions |  | District Wide |  |  |  |  | Number of basic schools supported. |  | x |  | x | x |  | x |  | 15,000.00 |  |  |  |  |  |  | DA |  |  |  | DA |  |
|  |  | Support to DEOC |  | Karaga |  |  |  |  | Number of DEOC meetings held |  | x |  | x | x |  | x |  | 5000 |  |  |  |  |  |  | GES |  |  |  | DA |  |
|  |  | Support monitoring of Circuit supervisors to education service delivery |  | karaga |  |  |  |  | Number of monitoring visists |  | x |  | x | x |  | x |  | 7000 |  |  |  |  |  |  | GES |  |  |  | DA |  |
| Health Delivery |  | Build the capacity of 30 CHV on IYCF |  | Selected communities |  |  |  |  | CHV capacities on IYCF improved |  |  |  |  | x |  |  |  |  |  |  |  |  | 23,000 |  | DHD |  |  |  | DA |  |
|  |  | Promote the use of mass media outreach |  | District Wide |  |  |  |  | Mass media outreach promoted |  | x |  | x | x |  | x |  |  |  |  |  |  | 10,137.20 |  | DHD |  |  |  | DA |  |
|  |  | Carry out cooking demonstrations on 4-star diet for 30 school feeding caterers |  | Selected caterers |  |  |  |  | Number of caterers and food vendors trained |  |  |  |  | x |  |  |  |  |  |  |  |  | 7,400.00 |  | DHD |  |  |  | DA |  |
|  |  | promote 20 No mother-to-mother support groups |  | Selected communities |  |  |  |  | 20No. mother to mother support groups established |  | x |  | x | x |  |  |  |  |  |  |  |  | 35,776.60 |  | GHS |  |  |  | DA |  |
|  |  | Carry out ENA monitoring for non-health workers |  | Selected staff |  |  |  |  | ENA monitoring for non-health workers carried out |  |  |  |  |  |  | x |  |  |  |  |  |  | 4,966.80 |  | GHS |  |  |  | DA |  |
|  |  | Carry out 8 Community durbars on GIFTS (out-of-school) and Vitamin A supplementation among children 12-59mths targeting approximately 100 people per session |  | Selected communities |  |  |  |  | Number of community durbars carried out |  |  |  |  |  |  | x |  |  |  |  |  |  | 3,400 |  | GHS |  |  |  | DA |  |
|  |  | Organize new and refresher training on Girls Iron-folate Supplementation (GIFTS) for 30 School-based Health teachers |  | Karaga |  |  |  |  | Number of teaches trained |  |  |  |  | x |  |  |  |  |  |  |  |  | 7,655 |  | GHS |  |  |  | DPCU/DA |  |
|  |  | Community Outreach Support and Home visiting on IYCF, GIFTS, CMAM in 33 communities |  | Selected communities |  |  |  |  | Number of communities |  |  |  |  |  |  | x |  |  |  |  |  |  | 6,930 |  |  |  |  |  |  |  |
|  |  | Deworm 1000 students in basic schools |  | Selected schools |  |  |  |  | Number of students dewormed |  |  |  |  |  |  | x |  |  |  |  |  |  | 3,280 |  | GHS |  |  |  | DA |  |
|  |  | Support to malaria prevention |  | District wide |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  | 15,000 |  |  |  |  | GHS |  |  |  | DA |  |
| Social Welfare and Community Development |  | Sensitization of PWDs on Nutrition sensitive activities |  | Selected communities |  |  |  |  | Number of PWDs sensitized |  |  |  |  | x |  |  |  |  |  |  |  |  | 3000 |  | CD&SW |  |  |  | DA |  |
|  |  | Carry out registration and monitoring of day-care centers in the district |  |  |  |  |  |  | Number of day-care centers registered and monitored |  |  |  | x |  |  |  |  |  |  |  |  |  | 4000 |  | CD&SW |  |  |  | DA |  |
|  |  | Formation and training of social protection committees members in 20 communities |  |  |  |  |  |  | Social protection committees formed and trained |  |  |  | x |  |  |  |  |  |  |  |  |  | 4000 |  | CD&SW |  |  |  | DA |  |
|  |  | Organize and train 20 women groups on income generating activities |  |  |  |  |  |  | 20 women groups organized and trained |  |  |  |  | x |  |  |  |  |  |  |  |  | 6000 |  | CD&SW |  |  |  | RING II |  |
|  |  | Create awareness on child labor in the district |  |  |  |  |  |  | Sensitization on child labor conducted |  |  |  |  | x |  |  |  |  |  |  |  |  | 5000 |  | CD&SW |  |  |  | WORLD VISION |  |
|  |  | Create awareness on child marriage in the district |  |  |  |  |  |  | Sensitization on child marriage conducted |  |  |  | x |  |  |  |  |  |  |  |  |  | 4000 |  | CD&SW |  |  |  | WORLD VISION |  |
|  |  | Monitor field activities |  |  |  |  |  |  | Field activities monitored |  |  |  | x |  |  |  |  |  |  |  |  |  | 392.00 |  | CD&SW |  |  |  | DA |  |
|  |  | Disbursed funds to PWDs to engaged in economic activities |  | District wide |  |  |  |  | Beneficiaries economic livelihood improved |  | x |  | x |  |  |  |  |  |  |  |  |  |  |  | CD&SW |  |  |  | DA |  |
|  |  | Payment of LEAP beneficiaries |  | District wide |  |  |  |  | Beneficiaries economic livelihood improved |  | x |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GENDER MAINSTREAMING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Mainstreaming gender concerns into all DA programs |  | DA |  |  |  |  | Gender mainstreaming improved |  | x |  |  |  |  |  |  | 500.00 |  |  |  |  |  |  | Gender unit |  |  |  | DA |  |
|  |  | Sensitize 150 women on nutrition |  | Selected communities |  |  |  |  | 150 women sensitized on nutrition |  |  |  |  | x |  |  |  |  |  |  |  |  | 1,700 |  | Gender unit |  |  |  | DA |  |
|  |  | Sensitize 10 communities on child rights |  | Selected communities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Organize 4 community forums for on preparation of nutrient rich food for households |  | Selected communities |  |  |  |  | Number of community foras organized |  |  |  |  |  |  | x |  |  |  |  |  |  | 8,420 |  | Gender unit |  |  |  | DA |  |
|  |  | Strenghten the capacity of 150 women on good nutrition through cooking Demonstration |  | Selected communities |  |  |  |  | Number of women capacities strenthened |  |  |  |  | x |  |  |  |  |  |  |  |  | 600 |  | Gender unit |  |  |  | DA |  |
|  |  | Sensitize 10 communities on Gender family model and Girl Child Education |  | Selected communities |  |  |  |  | Number of communities sensitized on the concept |  |  |  |  |  |  | x |  |  |  |  |  |  | 1,500 |  |  |  |  |  |  |  |
| Adopted Goal: Build a Prosperous Society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ECONOMIC DEVELOPMENT ( LED) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trade, Tourism and Local Economic Development |  | Business counseling |  | karaga |  |  |  |  | 60 clients counseled |  | x |  |  |  |  |  |  |  |  | 2,000 |  |  |  |  |  |  | BAC |  | DA |  |
|  |  | Group dynamics trianing |  | karaga |  |  |  |  | Number of Group members trained trained |  |  |  |  | x |  |  |  |  |  | 4,000 |  |  |  |  |  |  | BAC |  | DA |  |
|  |  | Promote VSLA groups in 20No. communities |  | District Wide |  |  |  |  | VSLA groups in 20No. Communities promoted |  | x |  | x | x |  | x |  |  |  | 5,200 |  |  | 9,313.20 |  |  |  | BAC |  | DA |  |
|  |  | Shea butter processors |  | Selected communities |  |  |  |  | Number of SMEs trained |  | x |  | x |  |  |  |  |  |  | 6000 |  |  |  |  |  |  | BAC |  | DA |  |
|  |  | Literacy and Numeracy training |  | Selected communities |  |  |  |  | Number of SMEs trained |  |  |  |  | x |  |  |  |  |  | 2000 |  |  |  |  |  |  | BAC |  | DA |  |
|  |  | Bee keeping |  | Selected communities |  |  |  |  | Number of SMEs |  |  |  |  | x |  |  |  |  |  | 6,000 |  |  |  |  |  |  | BAC |  | DA |  |
|  |  | Soap making Training |  | Tong |  |  |  |  | Training conducted |  |  |  | x |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  | BAC |  | DA |  |
|  |  | Bread making |  | Karaga |  |  |  |  | Number of SMEs supported |  |  |  | x |  |  |  |  |  |  | 6000 |  |  |  |  |  |  | BAC |  | DA |  |
|  |  | Marketing and Customer Relation |  | Selected communities |  |  |  |  | Number of Clients supported |  |  |  |  | x |  |  |  |  |  | 3,000 |  |  |  |  |  |  | BAC |  | DA |  |
|  |  | Soya Processing |  | Selected communities |  |  |  |  | Number of SMEs supported |  |  |  | x |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  | BAC |  | DA |  |
|  |  | Groundnut Processing |  | Selected communities |  |  |  |  | Number of trainings conducted |  | x |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  | BAC |  | DA |  |
|  |  | General Business management |  | Selected communities |  |  |  |  | Number of Businesses supported |  | x |  |  |  |  |  |  |  |  | 4,000 |  |  |  |  |  |  | BAC |  | DA |  |
|  |  | Buyer Requirements |  | Selected businesses |  |  |  |  | Number of Businesses with access |  |  |  | x |  |  |  |  |  |  | 4,000 |  |  |  |  |  |  |  |  |  |  |
|  |  | Carry out feasibility on potential tourism sites |  | District Wide |  |  |  |  | Feasibility on potential tourism sites carried out |  | x |  | x | x |  | x |  | 3,000.00 |  |  |  |  |  |  |  |  | DAD |  | DA |  |
| Adopted Goal: Safeguard the natural environment and ensure a resilient built environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DISASTER RISK MANAGEMENT AND CLIMATE CHANGE INTERVENTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Disaster Prevention and Management |  | Sensitization of 10 communities on the dangers of bush fires and disaster risk reduction |  | Selected communities |  |  |  |  | Disaster in the district reduced |  |  |  | x |  |  |  |  | 10,000.00 |  | 10,000 |  |  |  |  |  |  | NADMO |  |  | DA |
|  |  | Planting of trees in schools in the district |  | District Wide |  |  |  |  | Afforestation improved |  |  |  |  |  |  | x |  |  |  | 7,000 |  |  |  |  |  |  | NADMO |  |  | DA |
|  |  | Support to NADMO activities |  | Karaga |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  | 3,000 |  |  |  |  |  |  | NADMO |  |  | DA |
|  |  | Submission of Screening forms |  | District wide |  |  |  |  | Number of forms screened |  |  |  |  |  |  |  |  |  |  | 500 |  |  |  |  |  |  | DA |  |  | DA |
|  |  | Support the activities of forestry commission on Green Ghana Campaigns ( Tree planting) |  | District wide |  |  |  |  | Afforestation management improved |  |  |  | x |  |  |  |  |  |  | 21,000 |  |  |  |  |  |  | NADMO |  |  |  |
|  |  | Acquisition of EPA certificate |  | Karaga |  |  |  |  | EPA certificate acquired |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  | DA |  |  | DA |
|  |  | Support to Climate SMART Agriculture in the District |  | District wide |  |  |  |  | Number of trainings organised |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DDA |  |  | DA |
| Agriculture |  | Conduct Gaps training on backyard garden establishment. Agri. house foundation |  | Selected communities |  |  |  |  | Training conducted |  | x |  | x |  |  |  |  |  |  | 4,000 |  |  |  |  |  |  | DDA |  |  | DA |
|  |  | Sensitization of farmers on the new PFJ implementation modalities |  | Selected farmers |  |  |  |  | Farmers sensitized |  | x |  | x |  |  |  |  |  |  | 3,000 |  |  |  |  |  |  | DDA |  |  | DA |
|  |  | Train farmers on compost preparation and its usage. |  |  |  |  |  |  | 140 farmer trained on compost preparation |  | x |  |  |  |  |  |  |  |  | 2,500 |  |  |  |  |  |  | DDA |  |  | DA |
|  |  | Training farmers on good livestock management and proper husbandry |  |  |  |  |  |  | Trining conducted |  |  |  |  |  |  | x |  |  |  | 4000 |  |  |  |  |  |  | DDA |  |  | DA |
|  |  | Training farmers on value addition of farm produce. |  |  |  |  |  |  | Training conducted |  | x |  |  |  |  |  |  |  |  | 6000 |  |  |  |  |  |  | DDA |  |  | DA |
|  |  | Train sixty farmers on climate smart Agriculture |  |  |  |  |  |  | Farmers trained |  |  |  |  |  |  | x |  |  |  | 3000 |  |  |  |  |  |  | DDA |  |  | DA |
|  |  | Management of Beehives |  |  |  |  |  |  | Number of beehives managed |  |  |  |  | x |  |  |  |  |  | 7000 |  |  |  |  |  |  | DDA |  |  | DA |
|  |  | Train (30) farmers on Dry season vegetable production. |  |  |  |  |  |  | Number trained |  |  |  | x |  |  |  |  |  |  | 4000 |  |  |  |  |  |  | DDA |  |  | DA |

| Adopted Goal: Build a Prosperous Society |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ENVIRONMENTAL HEALTH AND SANITATION |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental health and sanitation | Sensitize and Screen food Vendors /School Feeding Caterers | Karaga |  | Food Vendors /School feeding caterers sensitized |  |  | x | x |  |  | 14,960.00 | EHSU | DA |
|  | Sensitize communities on hand washing with soap /ash | 30 communities |  | Communities sensitized on hand washing with soap/ash |  | x |  |  |  |  | 20,000.00 | EHSU | DA |
|  | Dislodge public toilets in the Districts (Liquid waste management) | 5 public toilets |  | 5 toilets dislodged |  | x |  |  |  |  | 36,475.00 | EHSU | DA |
|  | Organize quarterly clean up exercise | 4 small towns |  | Clean up exercise organized |  |  |  |  |  |  | 25,000.00 | EHSU | DA |
|  | Monitor food vendors and handlers | 150 Households |  | Food vendors and handlers monitored |  | x |  |  |  |  | 4,500.00 | EHSU | DA |
|  | Monitor the activities of sanitation service providers | District wide |  | Activities of sanitation service providers monitored |  | x |  |  |  |  | 4,800.00 | EHSU | DA |
|  | Monitor ODF communities to sustain ODF | 40 Communities |  | 40 communities sustained ODF | x |  |  |  |  |  | 44,000.00 | EHSU | Global Communities |
|  | Organize refresher training on WMSTs | 10 communities |  | WMSTs capacity built |  | x |  |  |  |  | 20,000.00 | EHSU | World Vision |